## SW Dev Plan
Phase | Task | Deliverable | Owner | Timeline (Weeks) | Status | start date | End date
Requirements | Gather functional safety requirements (ASIL-D) | FSR Document | Systems Engineer | 2 | Not Started | 2024-04-17 | 2024-04-29
Requirements | Define system & software requirements | SRS Document | SW Requirements Engineer | 5 | Not Started | 2024-01-22 | 2024-02-16
Design | Architectural design of Airbag ECU software | Software Architecture Document | SW Architect | 1 | Not Started | 2024-03-13 | 2024-04-06
Design | Detailed component design | Detailed Design Document | SW Developer | 2 | Not Started | 2024-03-01 | 2024-04-11
Implementation | Develop software modules | Source Code | SW Developer | 3 | Not Started | 2024-03-08 | 2024-03-24
Implementation | Unit testing and static analysis | Unit Test Report | SW Tester | 2 | Not Started | 2024-01-03 | 2024-02-05
Testing | Integration testing | Integration Test Report | Test Engineer | 3 | Not Started | 2024-06-11 | 2024-07-13
Testing | Validation against safety goals | Validation Report | Validation Engineer | 4 | Not Started | 2024-06-23 | 2024-07-22
Release | Final release & documentation | Release Notes | Release Manager | 1 | Not Started | 2024-04-26 | 2024-06-10